## Release T2 R2024.JUN Calendar
Line | Week number | Day/ Week/ Weekend | Start Date | End Date | Activity type | Activities | EAC | UTEST | PROD | Comments
1 | 46 | Day | 2023-11-17 | 2023-11-17 | Release scope | T2-WG proposes updated draft baseline release scope and change requests pending detailed assessments (DAs)
2 | 18 | Weeks | 2023-05-02 | 2023-10-11 | Release scope | 4CB completes CR detailed assessments/PBI feasibility assessments (including cross-service impact assessments where relevant)
3 | 46 | Week | 2023-11-17 | 2023-11-24 | Release scope | T2-TRSG: assessment implementation feasibility of initial scope
4 | 47 | Day | 2023-11-24 | 2023-11-24 | Documentation | Delivery of non-binding XSDs in MyStandards for the T2-WG community | E
5 | 48 | Weeks | 2023-11-28 | 2023-12-20 | Release scope | T2-WG proposes updated baseline release scope and STP
6 | 51 | Weeks | 2023-12-21 | 2024-01-11 | Release scope | Scope baseline & STP approved by the MIB |  |  |  | Updated scope/STP to be approved
7 | 2 | Day | 2024-01-10 | 2024-01-10 | Documentation | Publication date for binding XSDs in MyStandards for the T2-WG community | E
8 | 2 | Day | 2024-01-11 | 2024-01-11 | Documentation | Delivery of draft Release Note | E
9 | 3 | Day | 2024-01-15 | 2024-01-15 | Release scope | Publication date for draft Scope defining set of documents (T2 and Common Components) | E
10 | 3 | Day | 2024-01-18 | 2024-01-18 | Documentation | Delivery of final Release Note | E
11 | 3 | Weekend | 2024-01-19 | 2024-01-19 | Release deployment | Start release deployment to EAC (Package 0) | E
12 | 5 | Weekend | 2024-02-02 | 2024-02-02 | Release deployment | Deployment of Package 1 to EAC | E
13 | 7 | Weekend | 2024-02-16 | 2024-02-16 | Release deployment | Deployment of Package 2 to EAC | E
26 | 8 | Day | 2024-02-22 | 2024-02-22 | Release scope | Latest publication date for updated Scope defining set of documents (T2 and Common Components)
14 | 9 | Weekend | 2024-03-01 | 2024-03-01 | Release deployment | Deployment of Package 3 to EAC | E
15 | 11 | Weekend | 2024-03-15 | 2024-03-15 | Release deployment | Deployment of Package 4 to EAC | E
17 | 12 | Day | 2024-03-22 | 2024-03-22 | Documentation | Delivery of draft Release Note | E
18 | 13 | Day | 2024-03-27 | 2024-03-27 | Documentation | Delivery of final Release Note | E
19 | 13 | Weekend | 2024-03-28 | 2024-03-28 | Release deployment | Deployment of Package 5 to EAC | E
20 | 14 | Day | 2024-04-02 | 2024-04-02 | Reporting | Service Transition Status Report (STSR) for T2 R2024.JUN in Pre-Production (cut-off and delivery to TRSG and SMSG)
22 | 14 | Day | 2024-04-03 | 2024-04-03 | Reporting | T2-WG Go / No-go decision to deploy T2 R2024.JUN to Pre-Production |  |  |  | 8 business days before UTEST deployment
21 | 14 | Day | 2024-04-03 | 2024-04-03 | Documentation | T2-WG/RMCG approval of the security assessment and STSR for T2 R2024.JUN in Pre-Production
23 | 14 | Day | 2024-04-05 | 2024-04-05 | Documentation | Publication of draft Release Note |  | U
24 | 15 | Day | 2024-04-11 | 2024-04-11 | Documentation | Publication of final Release Note |  | U
25 | 15 | Day | 2024-04-12 | 2024-04-12 | Release deployment | Deployment of Package 6 to EAC | E
27 | 15 | Day | 2024-04-12 | 2024-04-12 | Release deployment | Start release deployment to Pre-production |  | U
28 | 15 | Weeks | 2024-04-12 | 2024-05-20 | Release testing | R2024.JUN Release testing |  | U
29 | 15 | Day | 2024-04-12 | 2024-04-12 | Release deployment | Deployment of Package 1, 2, 3, 4, 5 and 6 to Pre-Production |  | U
30 | 16 | Day | 2024-04-19 | 2024-04-19 | Release deployment | Deployment of Package 7 to EAC and Pre-Production | E | U |  | RD only
31 | 17 | Day | 2024-04-26 | 2024-04-26 | Release deployment | Deployment of Package 8 to EAC and Pre-Production | E | U |  | RD only
32 | 18 | Day | 2024-05-03 | 2024-05-03 | Release deployment | Deployment of Package 9 to EAC and Pre-Production | E | U |  | RD only
33 | 19 | Day | 2024-05-10 | 2024-05-10 | Release deployment | Deployment of Package 10 to EAC and Pre-Production | E | U |  | Critical RD only
34 | 20 | Day | 2024-05-17 | 2024-05-17 | Release deployment | Deployment of Package 11 to EAC and Pre-Production | E | U |  | Critical RD only
35 | 21 | Day | 2024-05-20 | 2024-05-20 | Reporting | Delivery of the T2 R2024.JUN Information security assessment to RMCG
36 | 21 | Day | 2024-05-20 | 2024-05-20 | Reporting | SWP ready for PROD deployment
37 | 21 | Day | 2024-05-20 | 2024-05-20 | Reporting | Service Transition Status Report (STSR) for T2 R2024.JUN in Production (cut-off and delivery to TRSG and SMSG)
38 | 21 | Day | 2024-05-20 | 2024-05-20 | Release testing | End of testing of T2 R2024.JUN scope elements in Pre-Production
40 | 21 | Day | 2024-05-23 | 2024-05-23 | Reporting | T2-WG recommends the release deployment to Production |  |  |  | 11 business days before PROD deployment (OGPF)
39 | 21 | Day | 2024-05-24 | 2024-05-24 | Release deployment | Deployment of Package 12 to EAC and Pre-Production | E | U |  | Critical RD only
41 | 22 | Day | 2024-05-29 | 2024-05-29 | Reporting | MIB approves the release deployment to Production |  |  |  | 8 business days before PROD deployment (OGPF)
42 | 23 | Weekend | 2024-06-08 | 2024-06-08 | Release deployment | Start release deployment to Production |  |  | P
Formulas:
Week number = WEEKNUM([Start Date],1)